## Slide 1
OVERWATCH
PLAN OF ACTION & MILESTONES
AI-Powered Narrative-to-Structure Intelligence Pipeline
Three Parallel Lines of Effort
Find the Data • Build the AI POC • Integrate Maven Smart System
March 2026

## Slide 2
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
2 / 11
EXECUTIVE SUMMARY
THE CHALLENGE
Operational data exists as unstructured narratives — OPLANs, FRAGORDs, Intel reports. Manual extraction is slow, error-prone, and can't keep pace with decision timelines.
THE SOLUTION
Overwatch uses AI to transform narrative data into structured findings, tasking orders, and a knowledge graph — enabling real-time decision support across all domains.
LOE 1
Find the Data
Identify real data sources, formats, security constraints, and access paths
LOE 2
Build AI POC
Unclassified system using AI-generated scenario data to prove ingest and advisor capabilities
LOE 3
Maven Smart System
Integrate into the production Maven platform for operational use

## Slide 3
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
3 / 11
CURRENT STATE & LOE PROGRESS
LOE 1: Find & Define Data
15%
Active
Working S3/S5 exercise and past data now
CENTCOM/INDOPACOM outreach — awaiting response
Surveying existing Maven holdings
Defining data requirements for joint commands
LOE 2: Build AI POC
~65%
On Track for May
POC 1 (~85%): ingest → normalize → KG → map/Gantt
POC 2 (not started): gap detection, priority tracing, impact analysis
AI scenario generation pipeline operational
Knowledge graph: strategy → missions → assets & dependencies
Real-time simulation engine with orbital propagation
Sprint plan: harden → detect → surface → polish
LOE 3: Maven Smart System
15%
Active
AI doc generation underway in Maven (parallel to LOE 2)
Parsing real documentation for structured extraction
Ontology shaping from LOE 2 schema + emerging real data

## Slide 4
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
4 / 11
LOE 1: FIND & DEFINE THE DATA
Three concurrent tracks: discover what exists, define what we need, bridge the gap with available data
NOW
Discover
Working S3/S5 exercise and past data
Surveying existing Maven holdings
Pursuing CENTCOM/INDOPACOM POCs (blocked — no response)
Unit exports and informal data sharing
NOW
Define
What formats can the AI pipeline handle?
What structured data does Maven need?
What should commands produce for us?
Outputs become requirements doc back to commands
MAR–MAY
Bridge
Manually parse S3/S5 data to build schemas
Feed into Maven once pipeline established
Best case: data already structured in Maven
Fallback: AI ingest handles unstructured input
JUN ONWARD
Formalize
Requirements doc to joint commands
Establish persistent data feed pipelines
Machine-to-machine connections where possible
Scale ETL paths from source to Overwatch

## Slide 5
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
5 / 11
LOE 2: THE FULL PIPELINE
Unclassified POC using AI-generated scenario data — two proof of concepts targeting mid-May 2026
1
Generate Docs
AI creates scenario documents (OPLANs, orders, intel)
2
Ingest & Structure
Classify, normalize, extract entities and relationships
3
Knowledge Graph
Strategy → missions → assets & dependencies in a connected graph
4
Map & Gantt
Visualize operational picture: units on map, missions on timeline
5
Detect Gaps
Walk the graph: unmet dependencies, coverage gaps, time conflicts, ranked by priority
6
Impact Analysis
"What if we lose X?" — trace cascade through KG to missions & strategy priorities
POC 1 — NARRATIVE → STRUCTURE (~85%)
POC 2 — DECISION SUPPORT (not started)
SPRINT PLAN
MAR 27–APR 10
Harden POC 1
APR 10–25
Build detection engine
APR 25–MAY 9
Surface gaps & impacts
MAY 9–20
Polish + demo prep

## Slide 6
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
6 / 11
LOE 3: MAVEN SMART SYSTEM INTEGRATION
Building in parallel with LOE 2 — re-engineering the same concepts inside the operational Maven environment
NOW
Explore & Build
AI doc generation underway in Maven (parallel LOE 2)
Parsing real documentation for structured data
Learning platform capabilities by building in it
Palantir reps available for guidance as needed
APR–MAY
AI Pipeline + Ontology
Build Foundry transforms for ingest pipeline
Prototype AI document identification in AIP
Map LOE 2 patterns to Maven equivalents
Ontology takes shape as real data formats emerge
MAY–JUL
Application Layer
Build Overwatch dashboard in Workshop
Map/timeline views using platform geo tools
Decision support workflows from LOE 2 POC 2
Refine ontology with LOE 1 real data
JUL–SEP
Operational Testing
User acceptance testing with operators
Performance validation at operational scale
Security review and accreditation prep
Operator training and documentation

## Slide 7
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
7 / 11
INTEGRATED TIMELINE
MAR
APR
MAY
JUN
JUL
AUG
SEP
MAR 26
POC DUE
LOE 1
Find Data
Requirements Discovery
Expand Data Access & Connectivity
LOE 2
AI POC
POC Build & Demo
Follow-On Development (Shaped by POC Results)
LOE 3
Maven
Explore & Build
App Layer Build
Ops Testing

## Slide 8
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
8 / 11
DEPENDENCIES & CONVERGENCE
How the three LOEs feed each other to converge on an operational system
LOE 1: Find & Define
Discovers what data exists and defines what Overwatch needs. Requirements flow back to commands. Best case: data already structured in Maven.
LOE 2: AI POC
Air-gapped POC validates AI can handle format ambiguity. If data arrives structured, ingest becomes fallback insurance. Patterns transfer to Maven.
LOE 3: Maven
Building in parallel — not waiting for LOE 2. Re-engineering the same concepts inside Maven. Ontology shapes as real data and LOE 2 patterns converge.
KEY CROSS-LOE DEPENDENCIES
Dependency | From | To | Gate Date
Real data samples available | LOE 1 | LOE 2, 3 | Apr 2026
AI ingest patterns validated | LOE 2 | LOE 3 | May 2026
Maven ontology mapped to schema | LOE 3 | LOE 1, 2 | May 2026

## Slide 9
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
9 / 11
RISKS & MITIGATIONS
RISK / IMPACT
DESCRIPTION
MITIGATION
HIGH
Joint Command Access
CENTCOM/INDOPACOM outreach has not received response. Unit-internal data requests face friction — nobody has defined what we need yet.
Working S3/S5 exercise data in parallel. Escalate through leadership for introductions. LOE 1 outputs become the requirements doc.
HIGH
Unknown Data Formats
Real data formats remain unknown. Schemas built on doctrine assumptions. Best case (structured in Maven) vs worst case (raw unstructured) still TBD.
AI pipeline designed for format ambiguity. If data arrives structured, ingest is fallback insurance. Schemas refine iteratively.
MED
Maven Systems Knowledge
Team learning Maven platform while building. Ontology not formally mapped. No deep Palantir expertise on team.
Palantir reps available. Learning by building — not waiting for survey. LOE 2 schema provides validated reference.
MED
Systems Access
Some data sources require accounts or access authorizations still in progress.
Pursuing access requests in parallel. Relying on unit exports and shared data. Manual parsing of S3/S5 data to keep building.

## Slide 10
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
10 / 11
KEY MILESTONES & DECISION POINTS
Date | Milestone | LOE | Decision / Gate
Apr 15 | Leadership findings report: data landscape, LIMFACs, access needs | 1 | Deliver report to leadership; catalog S3/S5 + Maven holdings; request action on gaps
Apr 30 | Maven AI pipeline prototype; ontology draft from LOE 2 patterns | 3 | Confirm Maven viability; assess ontology alignment with real data
May 15 | POC 1 demo: ingest → KG → map/Gantt | 2 | Stakeholder review of narrative→structure pipeline
May 20 | POC 2: gap detection, priority tracing, impact analysis | 2 | Demonstrate decision support layer on structured data
May 31 | AI ingest patterns validated; Maven pipeline prototype | 2, 3 | Confirm AI patterns port to Maven AIP
Jun 1 | Maven MVP ready for exercise use | 3 | Validate against exercise scenario; confirm operator readiness
Jul 31 | Maven dashboard full MVP | 3 | Operator acceptance, begin UAT
Sep 30 | Deployment / Continued Development Decision | ALL | Deploy, continue development, or combine with System Delta 85 effort

## Slide 11
WAY AHEAD
IMMEDIATE ACTIONS (NEXT 30 DAYS)
1
Characterize S3/S5 exercise data and Maven holdings; escalate CENTCOM/INDOPACOM access through leadership
LOE 1
2
Harden POC 1 (ingest→KG→viz), build POC 2 (gap detection, priority tracing, impact analysis) for mid-May
LOE 2
3
Continue AI pipeline and doc parsing build in Maven; map ontology as real data formats emerge
LOE 3
4
Schedule mid-May POC review with stakeholders; define success criteria across all three LOEs
ALL
END STATE: A production-ready, AI-powered operational intelligence system running within Maven Smart System, ingesting real data and providing real-time decision support to Joint Force Commanders.
11 / 11