## Slide 1
OVERWATCH
PLAN OF ACTION & MILESTONES
AI-Powered Narrative-to-Structure Intelligence Pipeline
Three Parallel Lines of Effort
Find the Data • Build the AI POC • Integrate Maven Smart System
March 2026

## Slide 2
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
2 / 11
EXECUTIVE SUMMARY
THE CHALLENGE
Operational data exists as unstructured narratives — OPLANs, FRAGORDs, Intel reports. Manual extraction is slow, error-prone, and can't keep pace with decision timelines.
THE SOLUTION
Overwatch uses AI to transform narrative data into structured findings, tasking orders, and a knowledge graph — enabling real-time decision support across all domains.
LOE 1
Find the Data
Identify real data sources, formats, security constraints, and access paths
LOE 2
Build AI POC
Unclassified system using AI-generated scenario data to prove ingest and advisor capabilities
LOE 3
Maven Smart System
Integrate into the production Maven platform for operational deployment

## Slide 3
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
3 / 11
CURRENT STATE & LOE PROGRESS
LOE 1: Find the Data
15%
Initiating
Focus: CENTCOM and INDOPACOM data sources
Surveying existing data in Maven Smart System
Candidate systems: JIST, GCCS, C2 / Intel DBs
Schemas designed on assumptions — refining as real data emerges
LOE 2: Build AI POC
~80%
On Track for May
Unclassified system using AI-generated scenario data
AI scenario generation pipeline operational
Document ingestion with type identification & normalization
Knowledge graph: strategy → missions → assets & dependencies
Real-time simulation engine with orbital propagation
AI decision advisor (COA, NLQ, impact assessment)
LOE 3: Maven Smart System
10%
Initiating
Platform access secured
Capability and tooling survey underway
Initial ontology concepts mapped from POC schema

## Slide 4
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
4 / 11
LOE 1: FIND THE DATA
Objective: Identify and access real operational data via CENTCOM, INDOPACOM, and Maven Smart System
MAR–MAY 2026
Access & Samples
Catalog candidate systems (JIST, GCCS, C2 / Intel DBs)
Survey existing data in Maven Smart System
Obtain samples via CENTCOM and INDOPACOM
Ongoing: pursue access requests in parallel
MAR–MAY 2026
Format Discovery
Map data formats (USMTF, OTH-Gold, VMF, Link 16)
Characterize security and access constraints
Validate AI ingest pipeline against real formats
Design schemas based on findings
MAY 2026
POC Integration
Simulate real data formats in unclassified environment
Validate structured output accuracy
Refine AI pipeline against discovered formats
Initial lay of the land complete
JUN ONWARD
Expand Data Access
Broaden connectivity to additional sources
Establish persistent data feed pipelines
Scale ETL paths from source to Overwatch
Performance benchmarking at scale

## Slide 5
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
5 / 11
LOE 2: BUILD THE AI PROOF OF CONCEPT
Unclassified POC using AI-generated scenario data to prove ingest and advisor capabilities by mid-May 2026
POC DELIVERY TARGET: MID-MAY 2026
MAR 26–APR 10
Stabilize document ingestion edge cases, refine review flag workflow
APR 10–25
Harden knowledge graph visualization, improve real-time update stability during ingestion
APR 25–MAY 5
End-to-end demo build: ingest document → structured data → map + Gantt display
MAY 5–12
Simulate LOE 1 data formats in unclassified environment; validate AI pipeline adaptability
MAY 12–20
Polish UI, fix remaining bugs, prepare POC demo package for stakeholder review
MAY 20–31
POC review, stakeholder demo, collect feedback to shape follow-on development priorities
KEY DELIVERABLE: AI ingest POC + AI advisor POC — learnings transfer directly to Maven Smart System build

## Slide 6
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
6 / 11
LOE 3: MAVEN SMART SYSTEM INTEGRATION
Objective: Build production Overwatch capability within Maven Smart System
MAR–APR
Survey & Foundation
Capability and tooling survey of Maven platform
Identify available connectors and AIP features
Begin ontology design from POC schema assumptions
Establish development environment and access
APR–MAY
Initial AI Pipeline
Begin building Foundry transforms for ingest pipeline
Prototype AI document identification in platform AIP
Map POC patterns to Maven equivalents
Initial POC milestone: demonstrate basic ingest capability
MAY–JUL
Application Layer
Build Overwatch dashboard in Workshop
Map/timeline views using platform geo tools
Decision support workflows
Refine ontology as real data formats emerge
JUL–SEP
Operational Testing
User acceptance testing with operators
Performance validation at operational scale
Security review and accreditation prep
Operator training and documentation

## Slide 7
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
7 / 11
INTEGRATED TIMELINE
MAR
APR
MAY
JUN
JUL
AUG
SEP
MAR 26
POC DUE
LOE 1
Find Data
Access & Format Discovery
Expand Data Access & Connectivity
LOE 2
AI POC
POC Build & Demo
Follow-On Development (Shaped by POC Results)
LOE 3
Maven
Survey
AI Pipeline
App Layer Build
Ops Testing

## Slide 8
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
8 / 11
DEPENDENCIES & CONVERGENCE
How the three LOEs feed each other to converge on an operational system
LOE 1: Find Data
Data formats and schemas inform both the AI harness design and the Maven ontology. Without characterization, downstream efforts build on assumptions.
LOE 2: AI POC
Unclassified POC validates AI can parse unknown formats. Proven identification and normalization patterns transfer to Maven AIP.
LOE 3: Maven
Production system consumes real data (LOE 1) using validated AI patterns (LOE 2) within the Maven Smart System environment.
KEY CROSS-LOE DEPENDENCIES
Dependency | From | To | Gate Date
Real data samples available | LOE 1 | LOE 2, 3 | Apr 2026
AI ingest patterns validated | LOE 2 | LOE 3 | May 2026
Maven ontology mapped to schema | LOE 3 | LOE 1, 2 | May 2026

## Slide 9
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
9 / 11
RISKS & MITIGATIONS
RISK / IMPACT
DESCRIPTION
MITIGATION
HIGH
Unknown Data Formats
Real operational data may use formats not yet encountered. Schemas designed on assumptions until real data arrives.
POC uses AI harnesses specifically designed for unknown formats. Two-phase identification adapts to new structures. Schemas refine iteratively.
MED
Data Access Delays
Security constraints or bureaucratic gates delay real data sample availability.
Continue POC development with synthetic and exercise data. Design AI pipeline to be format-agnostic. Pursue multiple data source paths in parallel.
MED
Maven Integration Complexity
Mapping POC schema to Maven ontology may reveal incompatibilities or require redesign.
Begin ontology mapping early (Mar). Use POC schema as validated reference. Leverage platform professional services.
LOW
AI Model Performance at Scale
LLM accuracy may degrade with noisy, real-world operational text vs clean training data.
Confidence scoring and review flags for human-in-the-loop validation. Iterative refinement as real data becomes available.

## Slide 10
OVERWATCH | PLAN OF ACTION & MILESTONES | MARCH 2026
10 / 11
KEY MILESTONES & DECISION POINTS
Date | Milestone | LOE | Decision / Gate
Apr 15 | Initial data samples obtained | 1 | Go/No-Go: real data access path confirmed
Apr 30 | Maven survey and ontology draft complete | 3 | Confirm Maven platform viability for Overwatch
May 15 | POC demo: ingest → map/Gantt | ALL | Stakeholder review; initial lay of the land across all 3 LOEs
May 31 | AI ingest patterns validated; Maven pipeline prototype | 2, 3 | Confirm AI patterns port to Maven AIP
Jul 31 | Maven dashboard MVP ready | 3 | Operator acceptance, begin UAT
Sep 30 | Initial Operational Capability (IOC) | ALL | Funding decision for FOC phase

## Slide 11
WAY AHEAD
IMMEDIATE ACTIONS (NEXT 30 DAYS)
1
Pursue CENTCOM/INDOPACOM data access; survey existing Maven data; obtain samples from JIST and C2 systems
LOE 1
2
Stabilize document ingestion and knowledge graph for end-to-end POC demo by mid-May
LOE 2
3
Complete Maven platform capability survey; begin ontology design and initial AI pipeline prototyping
LOE 3
4
Schedule mid-May POC review with stakeholders; define success criteria across all three LOEs
ALL
END STATE: A production-ready, AI-powered operational intelligence system running within Maven Smart System, ingesting real data and providing real-time decision support to Joint Force Commanders.
11 / 11